## Sheet1
Alien Escape
David Morton
13.2.2015
Task | Est Time (hours) | Actual time (hours) | Complete | Notes
Get png image rendering to the screen | 0.5 | 0.5 | 100% | issues with the SDL header files and libs folder
Add sprite class | 0.5 | 1 | 100% | problem with pointers when moving the texture class out of the main.cpp file
Add world manager | 0.25 | 1 | 100% | had to store a ref to the renderer for sprite class access
Add game manager | 0.25 | 1.5 | 100% | difficult move game loop to the game manager from the main.cpp file
Add keyboard input | 0.5 | 1 | 100%
Get the player sprite moving | 0.5 | 1 | 100% | issues with player in heriting the sprite class; player now holds info on sprite instance
Sprite animations | 0.5 | 2 | 100% | implmenting player animations in the player class caused reference issues when trying to render the clipped areas of the sprite sheet
Add timer for delta time | 0.5 | 0.5 | 100% | velocity value must be set high for player to move on screen
Move player by delta time | 0.25 | 0.25 | 100% | limited player left and right movements and reset position to lower left corner
Add gravity to game world | 1 | 2 | 100% | issues with gravity values
Add player jumping | 1 | 1 | 100% | because of SDLs origin poistion it took longer than expected to figure out the velocity values
Add gravity flipping | 0.5 | 0.5 | 100% | Added gravity direction value to the world manager for global access
Add renderer flipping for sprites | 1 | 0.5 | 100% | Change renderer flipping in world manager when gravity flips
Add debug info | 1 | 1 | 100%
Add player score to debug | 0.5 | 0.5 | 100%
Background image | 0.5 | 1 | 100%
Scroll background images | 0.5 | 0.5 | 80% | Issues with gap between the background images
Collision Manager | 0.5 | 0.5 | 100% | Implemented collision detection into nodes and World Manager
State Management | 0.5 | 1 | 100%
Sprite frame coming from XML file | 1 | 3 | 100%
Menu scene configuration from XML | 1 | 2 | 100%
Game Scene config XML file | 1 | 1 | 100%
Character state management | 1 | 2 | 100% | Check collision function needs pointer to other bounding box
UI elements from XML file | 1 | 2 | 100% | String searching through records and resources, names needed for each element
Implement HUD | 2 | 4 | 100% | Added scene class
Add pause functionality | 1 | 3 | 100% | HUD needed to be outside of the pause block, delta time pause